# Attachment B: Example Year 1 Work Plan
Community-Based Suicide Prevention Coalition Grant Request for Proposal

The work plan should include all anticipated goals, strategies, and action steps the organization intends to complete in the first year of the grant period. The work plan should reflect the overarching activity that is selected by the organization. Award recipients will be required to submit an annual work plan to MDH.

Additional strategies and action steps can be added to the tables, if needed. You may delete goals, strategies and action step rows as needed.

Goals: Goals are broad and should reflect the long-term expectations of what your organization hopes to achieve from this grant.

Strategies: Strategies describe the results you anticipate achieving and should support the goal. They should be clear, measurable, feasible, and appropriate for the scope of the project activity. SMART (Specific, Measurable, Achievable, Realistic, and Time-Bound) is a helpful way to develop your strategies. Often, multiple strategies are usually needed to address a single goal.

Action Steps: Action steps should be comprehensive and describe how the identified strategies will be achieved. For each action step, include a description with the expected timeline and staff/partners that will be involved. For staff/partners involved, please list either the name of the person or the position title who will be responsible for overseeing the action step.

## Workplan Timeframe:

| Organization Name: | Example Organization Name |
| --- | --- |
| Project Activity: | Community-Based Suicide Prevention Coalition |
| Population(s) Served: | Female youth ages 12-17 |
| Geographic Focus: | Example School District |

### Goal: Increase capacity for coalition building

| Strategy | Action Steps | Start Date | End Date | Staff Lead and Partners |
| --- | --- | --- | --- | --- |
| Hire 1.0 FTE to coordinate community coalition efforts | - Write job description - Post position - Hold interviews - Select candidate | July 2027 | August 2027 | Fiscal Host |
| Attend 3-day grant on-boarding meeting | - Attend 3-day grant on-boarding meeting - Book hotel room, if necessary. | September 2027 | September 2027 | Coordinator, Supervisor, Coalition Member |
| Attend Strategic Planning Sessions with MDH | - Attend quarterly sessions with MDH via Microsoft Teams | December 2027 | June 2028 | Coordinator, Coalition Members |

### Goal: Establish Community Coalition for the Grant

| Strategy | Action Steps | Start Date | End Date | Staff Lead and Partners |
| --- | --- | --- | --- | --- |
| Establish a multi-sector coalition that will assist with the implementation of this project. | - Recruit coalition members from a variety of sectors within the community. - Wrtie coalition bylaws to identify coalition name, membership responsibilities, how decisions will be made, and when and how often then coalition will meet. | July 2027 | December 2027 | Coordinator, Key Community Partners |
| If coalition is already established. | - Review coalition bylaws, update if necessary - Review coalition membership, develop a recruitment plan, if necessary. | July 2027 | December 2027 | Coordinator, Coalition Members |
| Schedule and hold monthly coalition meetings. | - Determine when and where the coalition will meet. | September 2027 | Ongoing | Coordinator, Coalition Members |

### Goal: Complete Community Assessment

| Strategy | Action Steps | Start Date | End Date | Staff Lead and Partners |
| --- | --- | --- | --- | --- |
| Define the community. | - Define the community in which the project will take place. | September 2027 | December 2027 | Coordinator, Coalition Members |
| Complete a community asset map. | - Determine plan for which coalition members will help with community asset mapping. - Determine what assets will be assessed. - Develop a template for what information will be gathered. - Finalize the community asset map. | September 2027 | December 2027 | Coordinator, Coalition Members |
| Gather community data to better understand the risk and protective factors of the priority population. | - Develop a plan to gather quantitative data. - Develop a plan to do community conversations to gather qualitative data. | December 2027 | March 2028 | Coordinator, Coalition Members, MDH Epidemiologist, MDH Evaluator |
| Analyze community asset map, qualitative and quantitative data to prioritize what will be addressed. | - Identify priority population of focus. - Prioritize risk and protective factors that will be addressed to promote mental health and prevent suicide. | December 2027 | March 2028 | Coordinator, Coalition Members |

### Goal: Select Strategies and Develop an Action Plan for Year 2

| Strategy | Action Steps | Start Date | End Date | Staff Lead and Partners |
| --- | --- | --- | --- | --- |
| Select strategies that will address the risk and protective factors that were prioritized. | - For each risk and protective factor, research strategies that have evidence of effectiveness and have a conceptual and practical fit. | March 2028 | June 2028 | Coordinator, Coalition Members |
| Develop an action plan for year 2 to implement the strategies that were selected. | Determine the following: - What tasks are needed to implement each strategy? - Who will carry out each of the tasks? - Timeline for each task - What resources are needed? - Communication on who needs to know what. | March 2028 | June 2028 | Coordinator, Coalition Members |
| Develop a capacity building plan for the coalition to help mobilize the work. | - If more members or specific skillsets are needed, develop a plan on how to address the gaps. - Determine what relationships may be necessary to implement the selected strategies. | March 2028 | June 2028 | Coordinator, Coalition Members, MDH Epidemiologist, MDH Evaluator |
| Develop budget for year 2 of the grant. | - Align the action plan to the proposed budget. | May 2028 | June 2028 | Coordinator, Coalition Members, Fiscal Host |

### Goal: Develop Evaluation Plan for year 2

| Strategy | Action Steps | Start Date | End Date | Staff Lead and Partners |
| --- | --- | --- | --- | --- |
| Develop an evaluation plan. | - Work with MDH to develop an evaluation plan to align with the strategies selected by the coalition. | May 2028 | June 2028 | Coordinator, Coalition Members, MDH Evaluator |